BONDED TERMINAL DIGITAL PLATFORM

Version 2 — Client Sign-Off Master Technical Specification

Functional, Technical, Operational, Security & Delivery Requirements

| Document Control | Value |
| --- | --- |
| Client | TRINU BONDED WAREHOUSE |
| Developer | Horizon Quantum Forge Limited |
| Document Reference | HQF-BTP-SPEC-002 |
| Version | 2.0 — Issued for Client Sign-Off |
| Date | 05 September 2026 |
| Status | For Client Approval / Development Baseline |
| Supersedes | HQF-BTP-SPEC-001 v1.0 and the original website brief |
| Classification | Confidential — Client and Developer only |

SIGN-OFF CONTROL: Development shall commence against this specification only after approval by authorised Client representatives. This document defines the agreed scope, functionality, exclusions, assumptions, dependencies, acceptance basis and Client responsibilities. Subsequent changes shall follow the Change Control procedure.

# Document Contents

1. Executive Summary

2. Purpose and Document Status

3. Business Objectives and Success Measures

4. Scope

5. Out of Scope and Deferred Scope

6. Stakeholders, Users and Roles

7. Regulatory, Customs and Compliance Position

8. Solution Principles

9. Solution Architecture

10. Cargo Lifecycle and State Machine

11. Public Website and CMS

12. Enquiry, Quotation, KYC and Onboarding

13. Identity, Access and Delegated Authority

14. Public Cargo Tracking

15. Stakeholder Portal

16. Document Management and Document Verification

17. Terminal Operating Core

18. Warehouse and Yard Management

19. Examination, Holds, Exceptions and Overstay

20. Gate and Vehicle Booking System

21. Tariff, Billing, Invoicing and Payments

22. Notifications and Messaging

23. Integration Layer

24. Customs / B’Odogwu Integration

25. Shipping Line and Carrier Integration

26. Payment, Messaging and Accounting Integrations

27. Terminal Hardware Integration

28. Interactive Terminal Map and Visualisation

29. Reporting, Analytics and Management Dashboards

30. Mobile and Offline Operations

31. Administration, Configuration and Audit

32. Data Model and Information Architecture

33. Security Architecture

34. NDPA and Data Protection

35. Content, UX and Design Requirements

36. Non-Functional Requirements

37. Technology Stack and Hosting

38. Infrastructure and Hardware Requirements

39. Quality Assurance and Testing

40. Deployment, Migration and Cutover

41. Training, Support and Maintenance

42. Delivery Phases and Milestones

43. Governance and Project Management

44. Change Control

45. Risks, Dependencies and Constraints

46. Assumptions

47. Client Responsibilities

48. Deliverables

49. Discovery Open Items

50. Acceptance Criteria

51. Module-Level Sign-Off

52. Final Execution and Signatures

# 1. Executive Summary

This documents consolidates the specification of business/website brief with the detailed Functional & Technical Specification into one client sign-off baseline. It defines the public digital experience, authenticated stakeholder services, Terminal Operating Core, operational workflows, integrations, security, data protection, infrastructure, testing, deployment, training and acceptance.

The platform is deliberately structured in three layers: Public Web, Stakeholder Portal and Terminal Operating Core (TOC). The TOC is the system of record; public and portal experiences consume controlled operational data rather than manually maintained status spreadsheets.

| Layer | Purpose | Primary users |
| --- | --- | --- |
| Public Web | Marketing, services, tracking, quote requests, FAQs, notices and contact. | Prospects, importers, agents, transporters, public |
| Stakeholder Portal | Authenticated cargo, documents, financials, bookings, notifications and requests. | Importers, agents, shipping lines/agents, transporters |
| Terminal Operating Core | Receiving, tally, yard/warehouse, examination support, gate, release controls, billing, integrations and audit. | Operations, gate, warehouse, documentation, finance, security, management, admin |

# 2. Purpose and Document Status

This document is the engineering, operational and acceptance baseline for the project. Discovery will confirm site-specific facts and close open items; it shall not silently alter the agreed scope.

| Item | Baseline |
| --- | --- |
| Requirements priority | M = Must; S = Should; C = Could. |
| Development | Build against signed baseline. |
| Discovery | Confirm processes, capacities, licences, tariffs, integrations, infrastructure and content. |
| Change control | Scope changes require written Change Request and approval. |
| Acceptance | UAT, defects, performance, security, accessibility, documentation and go/no-go criteria apply. |

# 3. Business Objectives and Success Measures

| ID | Objective | Target / Measure |
| --- | --- | --- |
| BO-01 | Reduce enquiry-to-quote time | Quote within 1 business day for 90% of requests. |
| BO-02 | Reduce status-enquiry calls | 60% reduction within 6 months of portal launch. |
| BO-03 | Reduce truck turnaround | Phase 2 baseline; target 25% reduction within 12 months. |
| BO-04 | Auditability | 100% of cargo movements have timestamped attributed audit entries. |
| BO-05 | Revenue leakage | 100% of chargeable events system-generated. |
| BO-06 | Release-document fraud | Every release authorisation independently verifiable at gate. |
| BO-07 | Technology positioning | Public tracking and portal live and accurate at launch. |

# 4. Scope

| Module | Scope | Phase |
| --- | --- | --- |
| M1 | Public website and CMS | 1 |
| M2 | Enquiry, quotation, KYC and onboarding | 1 |
| M3 | Identity, access and delegation | 1 |
| M4 | Public cargo tracking | 1 |
| M5 | Stakeholder portal | 1–2 |
| M6 | Document management and verification | 1–2 |
| M7 | Terminal Operating Core | 2 |
| M8 | Gate and truck appointment / VBS | 2 |
| M9 | Tariff, billing, invoicing and payments | 2 |
| M10 | Notifications and messaging | 1–2 |
| M11 | Integration layer | 2–3 |
| M12 | Reporting and analytics | 3 |
| M13 | Interactive terminal map | 3 |
| M14 | Administration, configuration and audit | 1–3 |
| M15 | Mobile and offline operations | 2–3 |

# 5. Out of Scope and Deferred Scope

Customs acts or decisions: assessment, valuation, classification, duty determination, examination decisions or Customs release authorisation.

General ledger, payroll, HR and procurement; the platform integrates with/export to accounting systems.

Physical hardware procurement and installation; hardware integration is possible but not in scope.

Terminal licensing, bond arrangements and regulatory approvals.

Legal drafting/approval of Customs and compliance wording.

Photography, video, drone footage, full copywriting and translation unless separately scoped.

Third-party subscription/transaction fees.

Historical migration unless data is supplied in the agreed template.

## 5.1 Deferred / candidate future scope

Native customer mobile applications and additional languages.

Automated yard optimisation.

Predictive dwell/congestion forecasting.

Terminal-to-terminal transfer network.

Public developer API programme.

Trade finance/insurance marketplace.

# 6. Stakeholders, Users and Roles

| Role | Primary Need / Responsibility |
| --- | --- |
| Prospect | Services, capability, cost basis, contact. |
| Importer / Consignee | Cargo status, documents, charges, release readiness. |
| Licensed Customs Agent | Act for authorised importers; multi-client delegated access. |
| Shipping Line / Agent | Manifest, container status, equipment interchange. |
| Transporter / Haulier | Slots, vehicles/drivers, gate passes, jobs. |
| Driver | Slot confirmation, gate pass, directions. |
| Terminal Operations | Execute and record cargo movements. |
| Gate Officer | Verify, ADMIT/REFER/REJECT, record movements. |
| Warehouse / Yard Officer | Receive, tally, locate, inspect, pick, relocate, issue. |
| Documentation Officer | Register/verify/issue documents. |
| Finance | Tariffs, invoices, collections, reconciliation. |
| Customer Service / Sales | Enquiries, quotes, onboarding and complaints. |
| Compliance / Customs Liaison | Regulatory interface and audit response. |
| Management | Throughput, revenue, utilisation, exceptions. |
| System Administrator | Users, roles, configuration, audit and integrity. |
| Regulator / Auditor | Scoped read-only access. |

# 7. Regulatory, Customs and Compliance Position

The platform shall operate within the Nigeria Customs Service Act 2023, applicable NCS procedures for bonded facilities and the Unified Customs Management System / B’Odogwu, the Nigeria Data Protection Act 2023 and applicable NDPC guidance, NCC requirements relevant to messaging, and the Client’s licence conditions and bond undertakings.

## 7.1 Mandatory wording controls

| Do not use | Use instead |
| --- | --- |
| We clear your cargo. | We support and coordinate the clearance process. |
| We release your cargo. | We release cargo once Customs authorisation and all terminal obligations are satisfied. |
| Customs examination by our team. | We provide facilities and coordination for Customs examination. |
| Duty payment. | Support with duty and charge payment processes. |
| Approved by Customs badge. | Only a specific licence/approval actually held, with reference. |

The Client supplies or legally approves all regulatory/Customs-facing copy. The Developer implements approved wording and does not author regulatory claims.

# 8. Solution Principles

One source of truth.

Events, not edits — immutable operational events.

Publish nothing that cannot be substantiated.

Mobile and low-bandwidth first.

Degrade, do not stop — offline operations.

Security and privacy by design.

Terminal facilitates; Customs decides.

Configurable business rules instead of hard-coded operational rules.

Evidence-backed operational records.

# 9. Solution Architecture

Reference flow: Internet/Mobile → CDN/WAF/DDoS/TLS → Public Web / Portal / Tracking / Staff Console / Offline Gate PWA → API Gateway (AuthN/AuthZ, rate limiting, audit, idempotency) → Domain Modules → Event Bus/Queue → PostgreSQL + Object Storage + Redis + Search + Audit Store + Analytics → Integration Adapters → NCS/B’Odogwu, shipping lines, payments, messaging, weighbridge, ANPR/CCTV/ACS and accounting.

| Decision | Baseline |
| --- | --- |
| Application | Modular monolith at launch with clean module boundaries and event bus. |
| Cargo lifecycle | Event-sourced; supporting domains use transactional CRUD with audit. |
| Public site | Server-rendered. |
| Portal/consoles | SPA with common versioned API. |
| Gate | Offline-first PWA with local queue and sync. |
| Integrations | Adapters, retry/backoff, circuit breakers, correlation IDs, DLQ and replay. |
| Documents | Object storage; DB metadata/hashes. |
| Hosting | Primary operational/personal data in Nigeria; DR separate Nigerian region/on-premises. |

# 10. Cargo Lifecycle and State Machine

| State | Meaning | Customer Label |
| --- | --- | --- |
| EXPECTED | Manifest/pre-advice received. | Expected |
| IN_TRANSIT_TO_TERMINAL | Controlled movement to terminal. | In transit to terminal |
| ARRIVED_AT_GATE | At gate, not accepted. | Arrived at terminal |
| RECEIVED | Accepted, tallied, condition recorded. | Received |
| STORED | Positioned; storage clock running. | In storage |
| DOCS_IN_PROGRESS | Documentation being registered/verified. | Documentation in progress |
| EXAMINATION_SCHEDULED | Examination booking confirmed. | Examination scheduled |
| UNDER_EXAMINATION | Presented for examination. | Under examination |
| EXAMINATION_COMPLETE | Outcome recorded. | Examination complete |
| HELD | Blocked by hold/dispute/documentation issue. | On hold — contact operations |
| CHARGES_PENDING | Terminal charges computed/unpaid. | Charges pending |
| CHARGES_SETTLED | Paid/credited. | Charges settled |
| RELEASE_AUTHORISED | Conditions satisfied; authority recorded. | Released for collection |
| SLOT_BOOKED | Collection appointment confirmed. | Collection booked |
| LOADING | Being loaded. | Loading |
| GATE_OUT | Departed. | Collected |
| CLOSED | Reconciled/archived. | Closed |
| OVERSTAYED | Permitted period exceeded. | Overstayed — action required |
| TRANSFERRED_OUT | Moved to approved facility. | Transferred |
| RETURNED / RE-EXPORTED | Exited via approved alternative route. | Returned / Re-exported |

## 10.1 Transition rules

Only configured transitions are allowed; illegal transitions are rejected.

Holds record type, authority, reason and reference; release from hold requires authorised actor and reason.

Release authorisation requires no active hold, required documentation and financial clearance or approved credit/waiver.

Every transition creates an immutable event and may trigger notification.

Storage clock starts at STORED and ends at GATE_OUT, with configurable free days and pause conditions.

Consignment, container and package tracking is supported; split/merge preserves lineage.

Bulk transitions may support per-unit exceptions.

State labels and customer wording are configurable.

# 11. Public Website and CMS

Homepage: positioning statement, Track Cargo, Request a Quote, Contact Operations.

Capability cards: Bonded Warehousing, Cargo Handling, Customs Support, Container Handling, Storage and Logistics.

Inline tracking, audience selector and latest notices.

How It Works: seven-stage journey Arrival → Documentation → Receiving → Secure Storage → Customs Processing → Release → Delivery.

Service pages with overview, inclusions, process, customer requirements, timelines, FAQs and quote CTA.

Cargo categories limited to those licensed/equipped: general, containerised, agricultural, industrial, automotive, project and special cargo as applicable.

Why Choose Us with verifiable facts.

Customs/compliance section, versioned customer guide and document library.

Audience landing pages for Importers, Customs Agents, Shipping Lines and Transporters.

Searchable FAQ, News & Notices, About Us, Careers (optional), Contact/Operations Centre.

CMS: WYSIWYG, media library, approval workflow, scheduling, version history, rollback, SEO controls, reusable blocks and preview.

# 12. Enquiry, Quotation, KYC and Onboarding

| Capability | Requirement | Priority |
| --- | --- | --- |
| Quote request | Company/contact, cargo, container count/size, weight/volume, arrival, storage duration, services, special requirements, attachments. | M |
| Progressive form | Relevant fields only; resumable via secure link. | M |
| Reference | Unique submission reference sent to user. | M |
| Anti-spam | Honeypot, rate limit and scoring. | M |
| Sales queue | New → Assigned → Quoted → Won/Lost, owner and SLA. | M |
| Quote builder | Tariff lines, quantities, durations, discounts, validity. | S |
| Quote acceptance | Branded/versioned PDF and online acceptance capturing identity, timestamp, IP and version. | S |
| KYC | CAC, TIN, licences where applicable, authorised signatories, verification checklist and approval. | M |
| Credit | Credit application, limit and finance approval. | S |
| Audit | Full enquiry-to-account history. | M |

# 13. Identity, Access and Delegated Authority

Self-registration with email/phone verification; pending until Client approval.

Organisation accounts with multiple users.

MFA mandatory for staff, finance and admin; strongly encouraged for trade users.

TOTP/SMS fallback and optional WebAuthn/passkeys.

Importer grants named agent access scoped by consignment/BL/container/time period and view/act permissions.

Delegation can be revoked instantly; agents see only active authorised records.

Session timeout, concurrent-session controls, device list and remote sign-out.

Breached-password screening, progressive lockout and reasoned admin unlock.

Joiner-mover-leaver workflow; optional LDAP/SAML/OIDC.

Break-glass access requires dual approval and alert.

Authentication, authorisation and delegation events logged.

# 14. Public Cargo Tracking

| Feature | Requirement |
| --- | --- |
| Lookup | Container, Bill of Lading or terminal reference. |
| Validation | Format hints and ISO 6346 check digit where applicable. |
| Public result | Status, timestamped timeline, terminal reference, next expected step. |
| Excluded | Consignee details, cargo value, invoice amounts, detailed goods description, storage location. |
| Protection | Rate limiting, enumeration protection, soft challenge. |
| Authenticated view | Full detail permitted by authorisation. |
| Notifications | Optional status change subscription via email/SMS/WhatsApp with double opt-in. |
| Shareability | Permanent tracking URL and QR deep link from terminal documents. |
| Future | SMS short-code/USSD fallback. |

# 15. Stakeholder Portal

## 15.1 Dashboard

Cargo in terminal/arriving/on hold/awaiting payment/ready/overstaying.

Action Required ranked by urgency and cost impact.

Outstanding balance, invoices, storage accrual and credit position.

Projected storage-cost exposure.

## 15.2 Cargo and service requests

Filter/sort/export cargo with saved views.

Consignment detail with containers, packages, weights, marks, description, arrival, location, status, event history, documents and charges.

Photographic evidence on receipt/damage/examination/loading.

Service requests for inspection, repackaging, sample drawing and additional handling.

Discrepancy/damage claims with evidence and tracking.

## 15.3 Documents and financials

Document repository and secure upload with validation/malware quarantine.

Required-document and expiry checklist.

Statement of account and invoice ageing.

Transparent live storage accrual.

Online payment initiation with provisional/confirmed receipts.

Proof-of-payment upload and finance confirmation.

Payment history and invoice dispute workflow.

# 16. Document Management and Document Verification

Every terminal-issued document is system-generated from controlled live data.

Unique reference, issue timestamp, issuing officer, QR and short verification code.

Public verification returns safe authenticity data only.

Digital signature/integrity control; altered documents fail verification.

Revocation immediately affects verification and gate checks.

Administrator-configurable versioned templates.

Bulk generation/download.

Retention and legal-hold controls.

Document access, verification and download events logged.

# 17. Terminal Operating Core

| Area | Requirements |
| --- | --- |
| Pre-advice/manifest | Manifest, EDI, CSV/XLSX or manual intake; duplicate detection. |
| Receiving/tally | Actual quantity, weight, marks, seal, condition, discrepancy and photographs. |
| Seal management | Seal at custody changes; mismatch exception requiring supervisor resolution. |
| Yard | Blocks, rows, slots, tiers; ground/stacked positions; movement history. |
| Warehouse | Zones, aisles, racks, bins; putaway, pick, relocate; bonded/non-bonded segregation. |
| Inventory | Real-time stock, cycle counts, stock-take, variance and approved adjustments. |
| Examination | Schedule, presentation, outcome/evidence, return to storage; no system-made Customs decision. |
| Stuffing/destuffing | Work orders, before/after reconciliation and lineage. |
| Value-added | Palletisation, repackaging, labelling, sorting, fumigation, weighing linked to charges. |
| Holds/overstay | Controlled hold workflow and automatic overstay flagging/escalation. |
| Handheld | Receiving, positioning, picking, inspection and scanning. |
| Configuration | Cargo types, services, locations, holds, reasons, roles and permissions configurable. |

# 18. Warehouse and Yard Management

Yard hierarchy: zone/block/row/slot/tier.

Warehouse hierarchy: zone/aisle/rack/bin.

Ground and stacked positions.

No double allocation of occupied positions.

Every movement creates an auditable event.

Bonded/non-bonded segregation.

Cycle counts and full stock-take with approved variance adjustments.

# 19. Examination, Holds, Exceptions and Overstay

| Capability | Requirement |
| --- | --- |
| Examination | Schedule/present/capture outcome/evidence/restore; competent-authority outcome only. |
| Hold types | Customs, agency, terminal, financial, damage, documentation. |
| Authority | Hold requires authority/reference, reason, actor and timestamp. |
| Exceptions | Central queue for seal mismatch, damage, discrepancy, failed gate checks and integration issues. |
| Overstay | Time-based flag, escalating customer notices and Customs-liaison report. |
| Overrides | Supervisor/authorised reason and audit trail. |

# 20. Gate and Vehicle Booking System

| Feature | Requirement |
| --- | --- |
| Slot booking | Date/time, consignment/container, vehicle and driver. |
| Capacity | Slot length, concurrent slots, cargo type, equipment and blackout periods. |
| Readiness | Validate cargo readiness and configured financial conditions. |
| Gate pass | Unique QR confirmation via portal/email/SMS/WhatsApp. |
| Amend/cancel | Configurable cut-off and no-show tracking. |
| Vehicle/driver | Plate, type, capacity, insurance/roadworthiness; driver licence/contact; expiry blocking. |
| Gate-in | QR or plate search; ADMIT/REFER/REJECT with reasons. |
| Override | Mandatory reason + supervisor approval; daily report. |
| ANPR | Optional plate recognition with manual fallback. |
| Gate-out | Release, seal and loaded quantity verification; exit pass and departure time. |
| Offline | Cached authorisation, queued transactions, sync and conflict reporting. |
| Turnaround | Gate-in to gate-out clock and reporting. |
| Access | Visitor/staff access separately recorded. |

# 21. Tariff, Billing, Invoicing and Payments

| Capability | Requirement |
| --- | --- |
| Tariff | Service/cargo/size/weight/customer group; effective dates/history. |
| Storage | Free period, unit, progressive escalation, minimum charge. |
| Pause | Authorised pause conditions. |
| Automatic charging | Chargeable operational events create charge lines. |
| Currency | NGN and optional foreign currency with conversion source/rate. |
| Tax | VAT/levies configurable per service. |
| Invoices | Pro-forma, final, credit note, receipt; sequential numbering. |
| Approvals | Discount/waiver/credit note thresholds and dual approval. |
| Payment | Card, bank transfer, USSD; signed webhooks and idempotency. |
| Reconciliation | Bank statement import and manual exception queue. |
| Credit | Limits, exposure and automatic block. |
| Clearance | Financial clearance consumed by release/gate. |
| Collections | Ageing, dunning and reminders. |
| Accounting | Export/API integration. |
| Audit | Rate changes, overrides, waivers and adjustments immutably logged. |

# 22. Notifications and Messaging

Event-driven templates.

Channels: in-app, email, and SMS.

Events: receipt, positioning, document issue, examination, holds, invoice, payment, release, slot, storage deadline, overstay, collection.

Per-user preferences and quiet hours.

Delivery status and retry.

Fallback channels.

Transactional/marketing distinction and opt-out.

Rate limiting/digest.

Internal alerts for SLA, exceptions, integration and security events.

# 23. Integration Layer

Common adapter interface with independent enable/disable.

Exponential retry/backoff and circuit breaker.

Correlation IDs and end-to-end logging.

Dead-letter queue and administrator replay.

Integration health dashboard.

Manual fallback for every integration.

Schema validation and quarantine of invalid inbound payloads.

Named Client owner, signed interface specification and test approach per integration.

# 24. Customs / B’Odogwu Integration

The NCS/B’Odogwu interface is dependent on access made available to terminal operators and Client/NCS approvals. Discovery shall establish the actual interface position.

| Target exchange | Baseline |
| --- | --- |
| Manifest/declaration reference | Validate/register relevant reference where authorised interface exists. |
| Status alignment | Align permitted upstream status references without asserting a Customs decision. |
| Examination | Record examination reference/scheduling data where available. |
| Release | Record Customs release authorisation reference/confirmation where available. |
| Manual gateway | Officer keys/scans authority reference with identity/evidence when no API exists. |
| Audit | All exchanges and manual authority references logged. |

The platform shall never make, infer or alter a Customs decision.

# 25. Shipping Line and Carrier Integration

Line API where available.

EDI support including BAPLIE, COPARN, CODECO, COARRI and COPRAR where applicable.

CSV/XLSX and manual fallback.

Outbound gate-in/gate-out/discharge/empty-return messages where accepted.

EIR generation/exchange.

Per-line transport, format and schedule configuration.

# 26. Payment, Messaging and Accounting Integrations

| Integration | Baseline |
| --- | --- |
| Payment | Selected Nigerian provider supporting required channels; final choice during Discovery. |
| Bank reconciliation | Virtual/dedicated accounts where supported; statement import fallback. |
| Email | SPF, DKIM, DMARC on Client domain. |
| SMS | Nigerian aggregator, delivery receipts and sender ID. |
| WhatsApp | Business API with approved templates. |
| Accounting/ERP | API adapter or scheduled export. |
| Customer master | Source-of-truth ownership agreed in Discovery. |

# 27. Terminal Hardware Integration

| Hardware | Requirement |
| --- | --- |
| Weighbridge | Serial/TCP weight-ticket capture with operator attribution. |
| ANPR | Plate-read events matched to bookings; manual fallback. |
| Barriers/ACS | Booking-validated commands, logged; manual override. |
| CCTV/VMS | Event bookmark/link; platform does not store/stream footage. |
| E-seals | Arm/disarm and alert events where deployed. |
| Handhelds | Android camera/laser scanning; final rugged model validated in Discovery. |

# 28. Interactive Terminal Map and Visualisation

| View | Requirement |
| --- | --- |
| Public | Gate → Inspection → Container Yard → Bonded Warehouse → Loading → Administration → Exit. |
| Zone details | Capacity, cargo types, security provisions and equipment from CMS/configuration. |
| Internal | Live occupancy, utilisation heat map and equipment position where available. |
| Security | No public camera/control-room/access-control detail. |
| Accessibility | Non-visual equivalent for all map information. |

# 29. Reporting, Analytics and Management Dashboards

| Class | Reports / Features |
| --- | --- |
| Operational | Cargo, receipts, releases, holds, exceptions, discrepancies, overstays, examinations, gate log. |
| Performance | Dwell, truck turnaround, gate throughput, utilisation, SLA attainment, inventory accuracy. |
| Financial | Revenue by service/customer, accruals, ageing, collections, discounts, waivers. |
| Compliance | Bonded stock, movement register, overstay register, audit extracts. |
| Management | Configurable date range, drill-down and trend comparison. |
| Distribution | Scheduled email. |
| Export | XLSX, CSV, PDF. |
| Access | Role-scoped; exports logged. |

# 30. Mobile and Offline Operations

Offline capability is a core operational requirement.

Responsive public/portal interfaces.

Mobile homepage: Track Cargo, Request Quote, Contact Operations, Book Truck Slot.

Installable portal PWA with optional push.

Android staff handheld for receiving, positioning, picking, inspection and gate.

Barcode/QR scanning.

Gate local authorisation cache and transaction queue.

Sync and conflict reporting after reconnection.

Lost-device protection: encryption, MDM, short cache and remote wipe where supported.

Explicit network-loss, upstream-outage, restart and sync-conflict tests.

# 31. Administration, Configuration and Audit

User/role/permission administration with approval/history.

Configuration console for designated business rules.

Searchable audit log by actor/entity/event/date/outcome.

Tamper-evident audit export.

Retention/purge with dry-run preview.

Feature flags.

Maintenance-mode and scheduled notices.

Time-boxed regulator/auditor read-only access.

Public metrics can be suppressed without code deployment.

# 32. Data Model and Information Architecture

| Entity | Core data / relationships |
| --- | --- |
| Organisation | Legal name, RC, TIN, licence, type, status, credit; users and consignments. |
| User | Identity, contact, role, organisation, MFA, status. |
| Delegation | Grantor/grantee, scope, permissions, validity. |
| Consignment | Terminal ref, BL, manifest ref, consignee, agent, arrival, description, status, holds. |
| Container | ISO, size/type, seals, weight, position, status. |
| Package | Marks, quantity, packaging, weight, dimensions, location. |
| Cargo Event | Type, from/to state, actor, time, location, device, reason, evidence. |
| Location | Zone, capacity, bonded flag, status. |
| Hold | Type, authority, reference, reason, raise/lift details. |
| Document | Type, reference, version, hash, signature, issuer, timestamps, storage key. |
| Tariff/Charge | Rate rules and charge lines linked to source event. |
| Invoice/Payment | Number, lines, totals, status, due date; payment/ref/reconciliation. |
| Booking/Gate | Slot, cargo, transporter, vehicle, driver, pass, decision, timestamps. |
| Audit | Actor, action, entity, before/after, time, IP, device, correlation/hash. |
| Notification | Recipient, event, channel, template, payload, status. |
| Content | Type, slug, body, version, status, publication and approvals. |

# 33. Security Architecture

| Threat | Primary Controls |
| --- | --- |
| Forged release documents | System-generated documents, signature, verification and gate validation. |
| Account takeover | MFA, session controls, delegation audit. |
| Insider manipulation | Immutable events, least privilege, approvals and override reporting. |
| Public enumeration | Minimal payload, rate limits and anti-bot controls. |
| Payment compromise | Gateway-hosted payment, signed webhooks, idempotency. |
| Malicious upload | Validation, malware scan, quarantine, non-executable storage. |
| DDoS | CDN/WAF/rate limiting. |
| Personal-data breach | Encryption, minimisation, access control, incident response. |
| Lost gate device | Encryption, MDM, short cache, remote wipe. |

## 33.1 Security controls

TLS 1.2 minimum / 1.3 preferred, HSTS, secure cookies and CSP.

Encryption at rest for database, object storage, backups and device caches.

Managed secrets; no credentials in source control/images.

Least privilege; no shared admin credentials.

OWASP Top 10/API Top 10 protection.

Input validation/output encoding/parameterised queries.

Dependency/container scanning; SAST/DAST.

Independent penetration test before production; critical/high remediation.

Incident response plan and vulnerability SLAs.

Administrative interfaces protected by network policy and MFA.

Short-lived tokens and revocation.

Security-event forwarding to Client SIEM where available.

## 33.2 Payment security

No cardholder data on Client-controlled systems.

Gateway-hosted or isolated SDK payment flow.

Verify webhook signatures and enforce idempotency.

Security/compliance reassessment for any architecture change.

# 34. NDPA and Data Protection

| Control | Requirement |
| --- | --- |
| Lawful basis | Recorded per purpose; consent captured/withdrawable where applicable. |
| Privacy notice | Published, versioned and timestamped. |
| Minimisation | No unnecessary personal fields. |
| Retention | Technical retention, purge/anonymisation and legal hold. |
| Data subject rights | Access, rectification, erasure, portability workflow with SLA. |
| Security | Encryption at rest; appropriate treatment of sensitive driver data. |
| Breach | Detection, escalation and 72-hour notification workflow where applicable. |
| DPIA | Discovery-stage assessment for ANPR/CCTV linkage/biometrics. |
| Processors | Appropriate processor agreements. |
| Residency | Primary personal and operational records within Nigeria; external processing requires assessment/safeguards. |

# 35. Content, UX and Design Requirements

Use Client brand assets; separate brand development if unavailable.

Deliver design system: tokens, typography, spacing, components, icons, motion.

Prefer real terminal imagery.

Status indicators use labels/shapes as well as colour.

Design coverage: homepage, journey, service, tracking, portal, consignment, quote, gate and mobile variants.

Two design revision rounds per screen set included.

Content matrix with owner/source/due date.

Plain-language customer guidance.

Client approval for regulatory claims.

# 36. Non-Functional Requirements

| ID | Target |
| --- | --- |
| NFR-001 Public LCP on 4G | ≤2.5s at 75th percentile |
| NFR-002 Homepage transfer | ≤1.2MB |
| NFR-003 Tracking | ≤1.5s at 95th percentile |
| NFR-004 Portal dashboard | ≤3.0s at 95th percentile |
| NFR-005 Online gate decision | ≤2.0s at 95th percentile |
| NFR-006 Offline gate decision | ≤1.0s local |
| NFR-007 Handheld scan | ≤1.5s at 95th percentile |
| NFR-008 Standard report | ≤10s for up to 12 months |
| NFR-009 API | ≤500ms at 95th percentile |
| NFR-010 Concurrent users | 500 |
| NFR-011 Organisations | 5,000 |
| NFR-012 Consignments/year | 100,000 |
| NFR-013 Events/day | 50,000 |
| NFR-014 Gate movements/day | 1,500 |
| NFR-015 Document growth | 500GB/year |
| NFR-016 Horizontal scaling | Required without web/API downtime |
| NFR-017 Peak headroom | 3× |
| NFR-018 Public availability | 99.5% monthly |
| NFR-019 Portal/API | 99.5% monthly |
| NFR-020 Gate/ops effective availability | 99.9% |
| NFR-021 RTO | 4 hours |
| NFR-022 RPO | 15 minutes |
| NFR-023 Backups | Hourly incremental, daily full, 30-day retention, monthly archive 12 months |
| NFR-024 Restore tests | Quarterly |
| NFR-026 Accessibility | WCAG 2.2 AA |
| NFR-030 Operational touch targets | ≥48px; daylight usable |
| NFR-033 Browsers | Current + previous major Chrome/Edge/Firefox/Safari; mobile Chrome/Safari |
| NFR-034 Handheld | Android 10+ |
| NFR-035 Screens | 320–2560px |
| NFR-037 Logic coverage | ≥75%; 100% lifecycle/tariff engine |
| NFR-038 Logs | Structured JSON + correlation IDs |
| NFR-039 Observability | Metrics, tracing, alerts, runbooks |
| NFR-040 Infrastructure | IaC; no undocumented production configuration |
| NFR-041 Ownership | Client-owned source/IaC/document repository |
| NFR-042 Configurability | No hard-coded designated business rules |

# 37. Technology Stack and Hosting

| Layer | Recommended baseline |
| --- | --- |
| Public web | SSR: Next.js or PHP/ Laravel |
| Portal/consoles | React/Vue + TypeScript. |
| Backend | Laravel PHP 8.3+ or NestJS Node 22 LTS; final selection based on Client capability. |
| Database | PostgreSQL 16+. |
| Cache/queue | Redis + durable queue. |
| Object storage | S3-compatible. |
| Search | PostgreSQL FTS initially; Meilisearch/OpenSearch if required. |
| Offline | PWA + service worker + IndexedDB. |
| Runtime | Docker; Compose/Kubernetes. |
| CI/CD | Git-based automated pipeline. |
| Observability | Managed or self-hosted metrics/logs/traces. |

## 37.1 Hosting

| Option | Description |
| --- | --- |
| A — Nigerian cloud/colocation | Primary in Nigerian data centre; DR second Nigerian site; recommended baseline. |
| B — Hybrid | Operational core/data on-premises; public/portal in cloud. |
| C — International cloud with Nigerian residency | Requires documented transfer assessment and appropriate safeguards. |

# 38. Infrastructure and Hardware Requirements

Redundant internet: fibre + secondary LTE/satellite and failover.

Wi-Fi across gate/yard/warehouse/examination areas.

UPS and generator backup.

Secured communications/equipment room.

Structured cabling to gate/weighbridge.

Gate workstation/Tablet/printer.

Rugged Android handhelds and QR/barcode printers.

ANPR/controller where used.

Weighbridge interface where offered.

Barrier controllers, switches/APs/cabling/UPS.

Server hardware if on-premises.

Client bears recurring third-party service costs such as hosting, backup, SMS, WhatsApp, email, payment gateway, maps, monitoring and annual penetration testing unless otherwise agreed commercially.

# 39. Quality Assurance and Testing

Phase 0 test strategy agreed.

Unit/integration tests in CI.

Critical E2E: tracking, quote, registration/login, consignment, payment, slot, gate-in/out and release.

Performance tests against NFRs.

Security testing and independent penetration test.

Accessibility audit.

Cross-browser/device testing.

Offline/failure-mode testing.

Client scripted UAT.

Defect severity and resolution targets agreed.

UAT sign-off before each go-live.

# 40. Deployment, Migration and Cutover

Zero-downtime web/API deployment where applicable.

Backward-compatible DB migrations.

Tested rollback.

Release notes.

Client-supplied migration data in agreed template; validation tool and up to two rehearsals.

Parallel run for replaced operational processes.

Formal go/no-go.

Four-week hypercare after each phase, with daily stand-ups in week 1.

# 41. Training, Support and Maintenance

## 41.1 Training

Role-based training for operations, gate, warehouse, documentation, finance, customer service and admins.

Train-the-trainer.

Resettable training environment.

User guides and gate/handheld quick cards.

Ten common-task video walkthroughs.

Customer help centre.

Architecture, runbook, configuration, integration and DR documentation.

## 41.2 Support baseline — subject to separate support agreement

| Severity | Response | Resolution Target |
| --- | --- | --- |
| S1 Critical | 30 min | 4 hours |
| S2 High | 2 hours | 1 business day |
| S3 Medium | 1 business day | 5 business days |
| S4 Low | 2 business days | Next scheduled release |

## 41.3 Maintenance

Security patching within vulnerability SLA.

Quarterly dependency/framework updates.

Quarterly backup verification/restore test.

Quarterly capacity review.

Annual security review and penetration retest recommended.

Content review reminders.

# 42. Delivery Phases and Milestones

| Phase | Duration | Major Content |
| --- | --- | --- |
| 0 Discovery & Design | 3–4 weeks | Workshops, process maps, lifecycle, tariffs, integrations, DPIA, IA/UI, technical design, test strategy. |
| 1 Public Platform & Portal | 4–8 weeks | Website/CMS, enquiry/quote/KYC, identity/delegation, tracking, portal, verification, notifications, admin/audit, lightweight operations console. |
| 2 Operations/Gate/Revenue | 8–12 weeks | TOC, VBS, tariffs/billing/payments, offline gate, handheld, financial portal, notifications. |
| 3 Integration & Intelligence | 12–16 weeks | Customs/line/hardware/accounting adapters, reporting, map, public stats, management dashboards, optional native apps. |

Indicative total: 16–20 weeks from Phase 0 start, excluding Client review time, procurement lead times and third-party access approvals. Committed schedule is refined after Discovery.

| Milestone | Evidence |
| --- | --- |
| MS-1 | Specification signed |
| MS-2 | Discovery report/design pack accepted |
| MS-3 | Phase 1 UAT entry |
| MS-4 | Phase 1 go-live |
| MS-5 | Phase 2 UAT entry |
| MS-6 | Phase 2 go-live/parallel run complete |
| MS-7 | Phase 3 UAT entry |
| MS-8 | Final acceptance, handover and hypercare complete |

# 43. Governance and Project Management

| Forum | Frequency | Purpose |
| --- | --- | --- |
| Sprint review/demo | Every 2 weeks | Working software and feedback. |
| Project steering | Monthly | Progress, risk, budget, decisions. |
| Technical working group | As needed | Infrastructure, integration, security. |
| Operations working group | Weekly in Phase 2 | Process, configuration, training. |

A single Client Product Owner shall have day-to-day decision authority. Escalated decisions should be resolved within three business days or schedule adjusted.

# 44. Change Control

Written Change Request for scope/function/interface/timeline/cost changes.

Developer impact assessment within 5 business days covering effort, cost, schedule and risk.

Client approval/rejection/deferral in writing within 5 business days.

Approved change becomes numbered addendum.

No verbal scope changes.

UAT-stage enhancements deferred unless defects.

A defect is behaviour that does not match this specification. A change requests behaviour not described here.

# 45. Risks, Dependencies and Constraints

| Ref | Risk/Dependency | Impact | Mitigation |
| --- | --- | --- | --- |
| D-1 | Third-party access | High | Client obtains NCS/line/bank/hardware access; fallbacks. |
| D-2 | Hardware readiness | High | Client procurement/readiness plan. |
| D-3 | Client decisions/content | High | Product Owner and content matrix. |
| D-4 | Terminal infrastructure | High | Redundant connectivity/power/Wi-Fi before Phase 2 UAT. |
| R-1 | Customs API unavailable | Medium | Manual structured gateway baseline. |
| R-2 | Unreliable connectivity | High | Offline-first gate/handheld + redundant links. |
| R-3 | Undefined operations | High | Phase 0 mapping and configurable workflows. |
| R-4 | Tariff changes | Medium | Effective-dated tariff engine. |
| R-5 | Scope creep | Medium | Change control. |
| R-6 | Staff resistance | High | Operations involvement/training/hypercare. |
| R-7 | Content delay | Medium | Content matrix/phased publication. |
| R-8 | Payment reconciliation | Medium | Provisional/confirmed receipt and manual queue. |
| R-9 | Cyber incident | Very High | Security controls, pentest, incident response. |
| R-10 | Regulatory change | Medium | Configurable wording/workflows and reviews. |
| R-11 | Key-person dependency | Medium | Documentation/deputies. |
| R-12 | Unverifiable public claims | High | System-generated metrics only. |

# 46. Assumptions

Client will hold required licences/approvals before Phase 2 go-live.

Capacity assumptions confirmed in Discovery.

Tariffs supplied in documented form.

Processes available for mapping.

Brand assets exist or separately scoped.

Terminal infrastructure ready before Phase 2 UAT.

Client SMEs available for workshops/review/UAT.

Content supplied to matrix.

Single-site operation at launch.

English at launch.

# 47. Client Responsibilities

| Ref | Responsibility |
| --- | --- |
| CR-01 | Product Owner with decision authority. |
| CR-02 | SMEs for Discovery/review/UAT. |
| CR-03 | Approved content, imagery, brand assets, documents. |
| CR-04 | Legal approval of Customs/regulatory wording. |
| CR-05 | Third-party access, credentials and test environments. |
| CR-06 | Hardware/infrastructure procurement and maintenance. |
| CR-07 | Tariff structure and charging rules. |
| CR-08 | Migration data and validation. |
| CR-09 | Domain/DNS control. |
| CR-10 | Third-party service accounts in Client name. |
| CR-11 | UAT within agreed windows. |
| CR-12 | DPO/equivalent and applicable NDPC obligations. |
| CR-13 | Approve public statistics and basis. |
| CR-14 | Staff release time for training. |

# 48. Deliverables

| # | Deliverable | Phase |
| --- | --- | --- |
| 1 | Discovery report/process maps | 0 |
| 2 | DPIA | 0 |
| 3 | Information architecture/UI pack | 0 |
| 4 | Technical design/test strategy | 0 |
| 5 | Public website/CMS | 1 |
| 6 | Enquiry/quote/KYC/onboarding | 1 |
| 7 | Identity/access/delegation | 1 |
| 8 | Public tracking | 1 |
| 9 | Stakeholder portal | 1–2 |
| 10 | Document management/verification | 1–2 |
| 11 | Notification engine | 1–2 |
| 12 | Admin/audit | 1–3 |
| 13 | Terminal Operating Core | 2 |
| 14 | Gate/VBS/offline PWA | 2 |
| 15 | Tariff/billing/payment | 2 |
| 16 | Staff handheld | 2 |
| 17 | Integration adapters | 3 |
| 18 | Reporting/analytics | 3 |
| 19 | Interactive map | 3 |
| 20 | Source/IaC/Client repository | All |
| 21 | Guides/quick refs/videos | All |
| 22 | Admin/runbook/DR documentation | All |
| 23 | Training/train-the-trainer | All |
| 24 | Penetration-test evidence | Per phase |

# 49. Discovery Open Items

| ID | Open Item | Owner |
| --- | --- | --- |
| OI-01 | Licences/approvals and permitted cargo categories | Client |
| OI-02 | Lifecycle states/transitions | Both |
| OI-03 | Bonded storage period/overstay procedure | Client |
| OI-04 | Tariffs/free days/escalation | Client |
| OI-05 | NCS/B’Odogwu interface availability | Client Customs Liaison |
| OI-06 | Payment gateway/banking | Client |
| OI-07 | Physical layout/zones/capacity/equipment | Client |
| OI-08 | Volume assumptions | Client |
| OI-09 | Hosting option | Both |
| OI-10 | Backend technology | Both |
| OI-11 | Public statistics/basis | Both |
| OI-12 | Support hours/coverage | Both |
| OI-13 | Existing systems/migration/integration | Client |
| OI-14 | Brand assets | Client |
| OI-15 | Accounting/ERP/source of truth | Client |
| OI-16 | Messaging providers | Client |
| OI-17 | Operating hours/holiday/maintenance rules | Client |
| OI-18 | UAT authorities/windows | Both |

# 50. Acceptance Criteria

All Must requirements for the phase demonstrated.

UAT scripts executed and signed.

No open S1/S2 defects; S3 has agreed dates.

Performance targets met/evidenced.

Security testing complete; no unremediated critical/high findings.

Accessibility audit complete with no unremediated primary-journey AA failures.

Documentation and training delivered.

Go/no-go assessed and passed.

## 50.1 Deemed acceptance

If the Client raises no written defects within ten business days of phase UAT release and the phase is placed into productive use, the phase may be deemed accepted subject to the commercial agreement.

| Severity | Definition |
| --- | --- |
| S1 | Critical function blocked; no workaround. |
| S2 | Significant function blocked or incorrect financial/cargo data; workaround exists. |
| S3 | Function impaired; acceptable workaround. |
| S4 | Cosmetic/minor inconvenience. |

# 51. Module-Level Sign-Off

| Module | Agreed | Comments / Conditions |
| --- | --- | --- |
| M1 Public Website & CMS | ☐ |  |
| M2 Enquiry, Quotation, KYC & Onboarding | ☐ |  |
| M3 Identity & Delegated Authority | ☐ |  |
| M4 Public Cargo Tracking | ☐ |  |
| M5 Stakeholder Portal | ☐ |  |
| M6 Document Management & Verification | ☐ |  |
| M7 Terminal Operating Core | ☐ |  |
| M8 Gate & Truck Appointment System | ☐ |  |
| M9 Tariff, Billing & Payments | ☐ |  |
| M10 Notifications & Messaging | ☐ |  |
| M11 Integration Layer | ☐ |  |
| M12 Reporting & Analytics | ☐ |  |
| M13 Interactive Terminal Map | ☐ |  |
| M14 Administration & Audit | ☐ |  |
| M15 Mobile & Offline Operations | ☐ |  |

# 52. Final Execution and Signatures

By signing this document, the Client confirms that the scope, functionality, exclusions, assumptions, dependencies, responsibilities, delivery approach and acceptance basis are understood and approved as the baseline for development. Subsequent changes shall follow the Change Control procedure.

| For and on behalf of TRINU BONDED WAREHOUSE | For and on behalf of Horizon Quantum Forge Limited |
| --- | --- |
| Name: ______________________________ | Name: ______________________________ |
| Position: ___________________________ | Position: ___________________________ |
| Signature: __________________________ | Signature: __________________________ |
| Date: ______________________________ | Date: ______________________________ |

| Approval Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Managing Director / CEO |  |  |  |
| Head of Terminal Operations |  |  |  |
| Head of IT / Technology |  |  |  |
| Compliance / Customs Liaison |  |  |  |
| Developer Project Lead |  |  |  |

END OF DOCUMENT — HQF-BTP-SPEC-002 v2.0